## Scenarios
| Overview -MANUFACTURING SCRIPTS |  | as of 27Dec2016
| Scripts | Descriptions | Tester 1 | Tester 2 | Tester 3 | Tester 4 | Tester 5 | Tester 6 | Tester 7 | Tester 8 | Tester 9 | Tester 10 | Tester 11 | Tester 12 | Tester 13 | Total | Passed | Failed | Tested | Remaining
1 | MFG001 | Product Data Management (Itemmaster)
2 | MFG002 | Product Data Management (itembranch)
3 | MFG003 | Product Data Management (workcenters)
4 | MFG004 | Product Data Management (rates)
5 | MFG005 | Product Data Management (Bill of Materials)
6 | MFG006 | Product Data Management (routings)
7 | MFG007 | Product Data Management (master routing/item X ref)
8 | MFG008 | PDM: mass update of components in bills
9 | MFG009 | Product Costing:Unit Cost and material burden
10 | MFG010 | Product Costing :Simulation and freeze
11 | MFG011 | Product Costing:Cost Copy to other branches
12 | MFG012 | MRP:Forecast Entry & update
13 | MFG013 | MRP:Defining branch relationships
14 | MFG014 | MRP: Itembranch configurations; MRP processing options; execution
15 | MFG015 | MRP:Convert Purchase Order messages in MRP
16 | MFG016 | MRP:Convert Work order messages in MRP
17 | MFG017 | WO:Process Workorders & attach partslist/routing. Add Serial numbers
18 | MFG018 | WO:Process WO material issues.
19 | MFG019 | WO:Process Workorders completions S line type SO. Add SN
20 | MFG020 | WO:Process Workorders completions W line type SO. Add SN
21 | MFG021 | WO:Time entry for repair or reflavor workorders
22 | MFG022 | WO:Process partial WO completions
23 | MFG023 | WO:Associating component SN to Parent SN
24 | MFG024 | WO:Understanding and using Phantoms
25 | MFG025 | WO:Shop Floor inquiries & Dispatch list, S&D Inquiry
26 | MFG026 | WO:Production Cost Inquiry & Manager's update to status=95
27 | MFG027 | WO:Process Repair Workorders
28 | MFG028 | WO:Process de-kitting workorders
29 | MFG029 | WO:Outside Operations
30 | MFG030 | WO:Component Scrap
31 | MFG031 | WO:Executing mfg related reports (shortages);(push/pull report)
32 | MFG032 | WO:Reversing WO completions
33 | MFG033 | WO:OneView Inquiries
34 | MFG034 | WO:Understanding forecast consumption (optional)
35 | MFG035 | WO:MRP (material requirement planning) net change
36 | MFG036 | WO:Lot holds and release
37 | MFG037 | WO:Perform Lot trace and track inquiry
38 | MFG038 | Mfg Actg.:Process manufacturing accounting (proof and final mode)
39 | MFG039 | Mfg Actg.:Process variance accounting: no variances (proof & final mode)
40 | MFG040 | Mfg Actg.:Process variance accounting: variances (proof & final mode)

## Blankets
|  |  |  | Branches | Item | Desc
Blanket PO and release |  |  |  | 800 | 14333-000 | BNDL,ADPT MOBIL ROBOT SW
| Responsibility | Process Outline | Doc #r/Type | Batch Number | Pass/ Fail | Tester Comments | Application¦Version | Version | Last Status | Next Status | Comments | Scheduler? | Reprint/Proof Version | On Demand Version | User Procedure | If Fail - Issue#
Tester 1
1 |  | Open Enter/change Blanket PO |  |  |  |  | P4310 | OAT0010
2 |  | Add new order for branch/ item/ quantity and cost | OB
3 |  | Save the blanket order | [6 empty] | 210 | 215
4 |  | Open release PO from blanket application | OP |  |  |  | P43216 | OAT0001
5 |  | Press find to locate your OB order
6 |  | Go to row exit to release purchase order. Enter quantity and date. Press save
7 |  | Go to form exist to release the purchase order. System will consolidate multiple items on same vendor | OP | [5 empty] | 220 | 280
8 |  | Process the OP order for print, per current process
END

## MFG001
MFG001
Product Data Management (Item master)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Create/copy new item master |  |  |  | P4101
2 |  | add/modify the item descriptions |  |  |  | P4101
3 |  | add/modify stocking type, line type, GLCode |  |  |  | P4101
4 |  | add/modify lot control values |  |  |  | P4101
5 |  | add/modify unit of measurements |  |  |  | P4101
6 |  | add/modify item notes |  |  |  | P4101
7 |  | add/modify planning parameters (addl system info) |  |  |  | P4101
END

## MFG002
MFG002
Product Data Management (Item Branch)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Create/copy new item branch record |  |  |  |  | P41026
2 |  | Select applicable branches |  |  |  |  | P41026
3 |  | verify or update GLCode, Stocking type, line type |  |  |  |  | P41026
4 |  | Update Planner, Buyer and Supplier address book numbers |  |  |  |  | P41026
5 |  | Define/verify Unit standard cost for purchased items |  |  |  |  | P41026
6 |  | Update UOM conversions |  |  |  |  | P41026
7 |  | Update lot control parameters (lot vs SN, shelf life) |  |  |  |  | P41026
8 |  | Update planning parameters (addl system info) |  |  |  |  | P41026
9 |  | Update planning parameters (Quantities) |  |  |  |  | P41026
END

## MFG003
MFG003
Product Data Management (WorkCenters)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Create/copy/review new work center |  |  |  | P3006
2 |  | define/update WC details |  |  |  | P3006
3 |  | Update parameters |  |  |  | P3006
4 |  | Define/update additional tabs (review is enough) |  |  |  | P3006
5 |  | Review various WCs under your branch |  |  |  | P3006
note: creating new WC require new BU. So you may just review existing ones
END

## MFG004
MFG004
Product Data Management (WorkCenters-rates)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Locate your workcenter |  |  |  | P3006
2 |  | highligh the row and go to row exit>rates |  |  |  | P3006
3 |  | Add/modify rates. Use 07 as default std cost method |  |  |  | P3006
4 |  | Review/modify the rates in simulated column |  |  |  | P3006
5 |  | Press Ok to save. Review the changes are saved |  |  |  | P3006
6 |  | Run WC rate Freeze update for the branch (MMCU) |  |  |  | R30860
7 |  | Review the output |  |  |  | P3006
8 |  | Go back to WC rates and verify frozen columns are updated |  |  |  | P3006
9 |  | optional: using data browser, user can export all data in F30008 table
WC rate freeze can be done at the time of cost rollup but prefer user doing when the simulated rates are modifed
END

## MFG005
MFG005
Product Data Management (Bill of materials)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Create/modify bill of materials. Enter your product and branch and press add or find |  |  |  | P3002
2 |  | Select to review the contents |  |  |  | P3002
3 |  | Add/modify components |  |  |  | P3002
4 |  | review start/end dates, issue type, featCost$/feat%plan values(should be 100%) |  |  |  | P3002
5 |  | verify/update operation seq#. This should be match routing number in routing data |  |  |  | P3002
6 |  | add/modify remarks fields if needed |  |  |  | P3002
7 |  | Save and verify |  |  |  | P3002
8 |  | Open the record again, highlight a component line and go to row exit for substitions |  |  |  | P3002
9 |  | Add/modify subsituted item with date range and quantities. Save the applications |  |  |  | P3002
10 |  | Optional: run bill of materials report for this item |  |  |  | R30460
END

## MFG006
MFG006
Product Data Management (Routings)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Create/modify Routing |  |  |  | P3003
2 |  | enter your product and find |  |  |  | P3003
3 |  | enter/update routing steps. Workcenter#, oper# (should match with data in bills), time basis(=U) and labor hours in run labor column |  |  |  | P3003
4 |  | Verify effective from and to dates. Add different routing steps. Apply setup, run labor and machine hours as applicable |  |  |  | P3003
5 |  | Optional: for outside operations step- enter PO reqd (Y/N), supplier# and costtype(D1) values
6 |  | Optional: run routing report |  |  |  | R30430
7 |  | verify the output
END

## MFG007
MFG007
Product Data Management (Master Routings and Item X-ref)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Create/modify new routing for generic master routing (item/branch record should be added for this master routing item with M type) |  |  |  | P3003
2 |  | add/modify routing steps with WC#, labor hours and effective from/to dates |  |  |  | P3003
3 |  | Save the data |  |  |  | P3003
4 |  | Open item X-ref application. Add MR X-ref type(this is hard-coded) and use master routing & your real product#. Do not use addressnumber |  |  |  | P4105
5 |  | press save.
For every new product/subs added, user have to come back to master routing to relate the record
END

## MFG008
MFG008
Product Data Management (Mass update of components across bills)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | **USE CAUTION**. This is an advanced UBE which will update/replace components across multiple bills. Always run this in PY/test environment first, after golive |  |  |  | R30520
2 |  | run the report from the menu. Verify/update data selection and processing option. Run the proof mode first |  |  |  | R30520
3 |  | Verify the output |  |  |  | R30520
4 |  | run the FINAL report from the menu. Verify/update data selection and processing option. |  |  |  | R30520
5 |  | Verify the output |  |  |  | R30520
6 |  | Open bills for impacted product and verify data has been updated |  |  |  | P3002
END

## MFG009
MFG009
Product Costing (Unit costs and material burden)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Inquire the purchased item from the item branch application |  |  |  | P41026
2 |  | goto row exit> costs |  |  |  | P4105
3 |  | press find to get existing records. Select the row to get into details |  |  |  | P4105
4 |  | Verify/update 08 cost method data for that item in the branch. This is branch specifi |  |  |  | P4105
5 |  | Save and verify |  |  |  | P4105
6 |  | Repeat the steps for other branches and other items |  |  |  | P41026
7 |  | Open Cost comp application for the final product or subs |  |  |  | P30026
8 |  | Find to get cost details |  |  |  | P30026
9 |  | Add/modify X1 cost method record for material burden. Burden could be a factor of material A1 cost and multiplication of two other factors. Ensure "&" symbol is used for factoring A1 costs |  |  |  | P30026
10 |  | press save and verify the simulated cost is updated. |  |  |  | P30026
End

## MFG010
MFG010
Product Costing (Cost simulation and Freeze)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Inquire costed bills for your parent item |  |  |  | P30206
2 |  | Inquire costed routings for your parent item |  |  |  | P30208
3 |  | Verify cost components for your parent item |  |  |  | P30026
4 |  | Execute cost simulation batch. Press OK on data selection and processing options |  |  |  | R30812
5 |  | Verify the output. Look for the new report that got generated from R30812 |  |  |  | R30825
6 |  | Verify cost components after cost simulation |  |  |  | P30026
7 |  | Execute cost freeze batch (proof mode) |  |  |  | R30835
8 |  | Verify the output |  |  |  | R30834
9 |  | Execute cost freeze batch (final mode) |  |  |  | R30835
10 |  | Verify the output. Look for the inventory impact from R30834 output |  |  |  | R30834
11 |  | Review Journal Entries. Approve/post |  |  |  | P0101
End

## MFG011
MFG011
Product Costing (Cost copy to other branches)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | **USER CAUTION**. This UBE cost components across multiple items in two branches. Run this in test/PY first, after go-live |  |  |  | P30206
2 |  | This UBE copy cost components for the products in other branches (non-sourcing). Let mfg branch be primary and others as secondary |  |  |  | R30890
3 |  | Run the report. Verify processing options for the right from and to branches |  |  |  | R30890
4 |  | Verify the output |  |  |  | R30890
5 |  | Run cost simulation for the secondary branches |  |  |  | R30825
6 |  | Execute cost freeze batch (proof mode) |  |  |  | R30835
7 |  | Verify the output |  |  |  | R30834
8 |  | Execute cost freeze batch (final mode) |  |  |  | R30835
9 |  | Verify the output. Look for the inventory impact from R30834 output |  |  |  | R30834
10 |  | Review Journal Entries. Approve/post |  |  |  | P0101
End

## MFG012
MFG012
Forecasting - manual update
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Manual Forecast Update |  |  |  | P3460
2 |  | Enter future forecast data for the products. Product#, date and quantity |  |  |  | P3460
3 |  | Update forecast data (previous data goes into original quantity) |  |  |  | P3460
4 |  | Decide on business process on forecast dates. Use forecast actuals to compare data. |  |  |  | R3465
END

## MFG013
MFG013
MRP-Defining branch relationships
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: for OSI spares order, system can transfer the demand to OAT automatically. For DRP/MRP to perform this action, branch relationships are required |  |  |  | P3403T
2 |  | Locate branch relationship application and press find |  |  |  | P3403T
3 |  | Locate the record for xxx-yyy relationships |  |  |  | P3403T
4 |  | Add new record for item level for testing/training sessions. Verify the effective from and to dates. Add transit time if needed. Press save |  |  |  | P3403T
branch relationships can be at item level or at MPF (master planning family level)
END

## MFG014
MFG014
Running MRP
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Optional: Verify planning parameters for key products. (item branch>addl system info & quantities apps)
2 |  | Optional: Verify MRP processing options. Refer training powerpoint guide.
3 |  | Execute MRP Regen batch |  |  |  | R3483
4 |  | Validate the data selections & processing options (do not change values)
5 |  | Review the out put (successful message) |  |  |  | R3483
6 |  | View Planning Messages |  |  |  | P3411
7 |  | View Supply/Demand for your item |  |  |  | P4021
8 |  | Optional:View pegging inquiry for parent demand |  |  |  | P4021
9 |  | Optional:View Time series for your item |  |  |  | P3413
10 |  | Optional:View Inventory availability |  |  |  | P41021
11 |  | Optional: Verify branch relationship, if there are no ST/OT orders |  |  |  | P3403T
END

## MFG015
MFG015
Process MRP messages for purchased items
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Open MRP message review application and filter data on item or planner or buyer |  |  |  | P3411
2 |  | Add filters on QBE for doc type=OP and message type= B or O | OP
3 |  | Modify the date or quantity by selecting the message. And save
4 |  | Highlight multiple message lines per vendor and click process messages
5 |  | Verify the message processed=Y updated
6 |  | Close the application for JDE to prompt with PO generation screen
7 |  | Verify the details and go to Form exit>generate PO
8 |  | Go to Row exit>PO revisions to verify the PO details (Supplier, item, quanitity and cost) | [5 empty] | 220 | 240
END

## MFG016
MFG016
Process MRP messages for make items
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Open MRP message review application and filter data on item or planner or buyer |  |  |  | P3411
2 |  | Add filters on QBE for doc type=WO and message type= B or O | WO
3 |  | Modify the date or quantity by selecting the message. And save
4 |  | Highlight multiple message lines, go to row exit and click process messages
5 |  | Verify the message processed=Y updated
6 |  | Verify the order number generated by the system | [6 empty] | 10
7 |  | Open Enter/Change WO and inquire these MRP generated work orders
END

## MFG017
MFG017
Process WO- Attach PL/Rtg
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Locate the MRP processed WO in Enter/Change WO application |  |  |  | P48013
2 |  | OR: Enter new WO in the application |  |  |  | P48013
3 |  | Enter item#, Quantity and requested date. Press Save to generate WO number | WO |  |  | P48013
4 |  | Execute attach Partslist/Routing batch R31410. On the data selection enter your WO# as literal |  |  |  | R31410
5 |  | Once the job is completed, review 'view job status', the outputs generated
6 |  | WO print: R31415 |  |  |  | R31415
7 |  | WO shortage report: R31418 |  |  |  | R31418
8 |  | WO summary report: R31416 (IF applicable) |  |  |  | R31416
9 |  | Generating Serial Number for items: Locate WO in WO Entry application. Go to row exit>Serialnumbers. Go to form exit> generate SN and press save |  |  |  | P3105
END

## MFG018
MFG018
Process WO- Material issues
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | assumption: WO is created and PL/Rtg attached. If you need to hard-commit location/SN, do it in the WO partslist application
2 |  | Locate your order in WO issues application. |  |  |  | P31113
3 |  | Select the line. On the details, verify the components that are being manually issued. Change loc/SN if needed (OR) pick loc/SN | WO |  |  | P31113
4 |  | When you search location, system will be ALL onhand inventory lines. You can issue direct from WH loc or from PRD location. |  |  |  | P31113
5 |  | Optional:On the SN components, go to row exit and associate the partent SN |  |  |  | P31113
6 |  | if you are NOT issuing certain parts, put 0 in issue field (OR) blank out the quantity issued field |  |  |  | P31113
7 |  | Press SAVE |  |  |  | P31113
END

## MFG019
MFG019
Process Workorders: Completions S line type
(example: sub-assemblies)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | :WO completion starts with manual issues of certain items and then super-backflush to complete the order |  |  |  | P31113
2 |  | On Inventory issues, locate your order and press find. Select to start material issues. Change quantity, if required and save |  |  |  | P31113
3 |  | Locate the WO# in the WO Super back flush application |  |  |  | P31123
4 |  | Press select to process the workorders. Enter quantity completed at routing operation and save |  |  |  | P31123
5 |  | WO issues and WO labor applications are in blind mode in this example | WO |  |  | P31123
6 |  | Optional: This screen does not show up per current configurations. On WO issues screen, review and save the transaction. On the WO labor screen, review and save the transaction |  |  |  | P31123
7 |  | On the final screen, enter the location on the second tab. For Serial numbered items, retrieve the serial number. Row exit>serial number and select the appropriate number. If SN is not generated, then generate a new one now |  |  |  | P31123
8 |  | WO completed qty and status validation: Go to WO entry screen and verify the WO status & compelted quantity fields |  |  |  | P48013
9 |  | Inventory transaction validation: Go to item ledger (cardex) and locate IC & IM transaction for this order |  |  |  | P4111
END

## MFG020
MFG020
Process Workorders: Completions for W line type
(example: Finished goods that are in sales orders)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | WO completion starts with manual issues of certain items and then super-backflush to complete the order |  |  |  | P31113
2 |  | On Inventory issues, locate your order & press find. Select to start Matl. issues. Change qty, if required & save |  |  |  | P31113
3 |  | Locate the WO# in the WO Super back flush application |  |  |  | P31123
4 |  | Press select to process the workorders. Enter quantity completed at routing operation and save |  |  |  | P31123
5 |  | For testing, WO issues and WO labor application will be prompted. In production system, this can be done blind mode | WO |  |  | P31123
6 |  | On WO issues screen, review and save the transaction. On the WO labor screen, review and save |  |  |  | P31123
7 |  | On the final screen, enter the location on the second tab. For SN items, retrieve the serial number. Row exit>serial number and select |  |  |  | P31123
8 |  | WO completed qty and status validation: Go to WO entry screen and verify the WO status & compelted quantity fields |  |  |  | P48013
9 |  | Inventory transaction validation: Go to item ledger (cardex) and locate IC transaction for this order |  |  |  | P4111
10 |  | Inventory transaction validation: Go to item ledger (cardex), locate IM data |  |  |  | P4111
11 |  | Sales order transaction validation: Verify the SO status is 530-535 status |  |  |  | P42010 |  |  | 530
END

## MFG021
MFG021
WO time entry for repair or reflavor type Workorders
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: you want to capture the time spent on WR type orders, which didn't had routings. Super backflush does not happen to these orders. Supervisor can manually enter the time spent for better cost absorption
2 |  | Open WO time entry application |  |  |  | P311221
3 |  | Enter the WR order number and press ADD. Enter employee number, shift and labor type. Enter the actual hours spent (either as total hour/min or start/end time). Save the transaction
4 |  | Open the transaction again, go to form exit and press update. This is a manual step for training/testing to capture the labor cost. In production system, there will be scheduler job
5 |  | If you open WR workorder and go to routing application, you can see the reported hours so far. If you have missed or overstated hours, you can do the correction by repeating the process
END

## MFG022
MFG022
Process Workorders: Partial completions
(example: sub-assemblies)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Optional:WO completion starts with manual issues of certain items and then super-backflush to complete the order |  |  |  | P31113
2 |  | Optional:On Inventory issues, locate your order and press find. Select to start material issues. Change quantity, if required and save |  |  |  | P31113
3 |  | Locate the WO# in the WO Super back flush application |  |  |  | P31123
4 |  | Press select to process the workorders. Enter quantity completed (partial order)at routing operation and save |  |  |  | P31123
5 |  | WO issues and WO labor applications are in blind mode to reflect real-life work. | WO |  |  | P31123
6 |  | Optional: This screen does not show up per current configurations. On WO issues screen, review and save the transaction. On the WO labor screen, review and save the transaction |  |  |  | P31123
7 |  | On the final screen, enter the location on the second tab. For Serial numbered items, retrieve the serial number. Row exit>serial number and select the appropriate number. If SN is not generated, then generate a new one now |  |  |  | P31123
8 |  | WO completed qty and status validation: Go to WO entry screen and verify the WO status & compelted (PARTIAL) quantity fields |  |  |  | P48013
9 |  | Inventory transaction validation: Go to item ledger (cardex) and locate IC transaction for this order |  |  |  | P4111
10 |  | Inventory transaction validation: Go to item ledger (cardex) and locate IM transaction for this order |  |  |  | P4111
END

## MFG023
MFG023
Associating component SN to Parent SN
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Locate the WO# in the WO Super back flush application |  |  |  | P31123 |  |  | 40
2 |  | Press select to process the workorders. Enter quantity completed at routing operation and save |  |  |  | P31123 |  |  | 10
3 |  | For testing, WO issues and WO labor application will be prompted. In production system, this can be made into blind mode | WO |  |  | P31123
4 |  | On WO issues screen, review and save the transaction. On the WO labor screen, review and save the transaction |  |  |  | P31123 |  |  | 40
5 |  | On the final screen, enter the location on the second tab. For Serial numbered items, retrieve the serial number. Row exit>serial number and select the appropriate number |  |  |  | P31123 |  |  | 90
6 |  | When both parent and component are serialnumber controlled, use the SN association application from row exit. Identify the SN of the components related to this parent item |  |  |  | P3107
7 |  | WO completed qty and status validation: Go to WO entry screen and verify the WO status & compelted quantity fields |  |  |  | P48013
END

## MFG024
MFG024
Understanding phantoms
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: phantoms are placeholder levels in bills to quickly identify or reuse that stage of the product at another assembly. No routings allowed at phantom level
2 |  | Add/modify phantom part in item master and branch with stocking type 0 (zero) |  |  |  | P41026
3 |  | Enter/change bills of materials taking phantom item as parent. Add components to this phantom level | WO |  |  | P3002
4 |  | Enter/change the final product and include phantom as one of the component |  |  |  | P3002
5 |  | Query the final product and using bill inquiry mode review how the phantom items are reflected |  |  |  | P3002
6 |  | Create WO for the final product. WO partslist will hide the phantom but include the component to the top level |  |  |  | P3002
END

## MFG025
MFG025
Shopfloor Inquiries
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: query open workorders and status of the workorders |  |  |  | P48013
2 |  | Using Shopfloor workbench, query orders by status range and requested date. You can use <'date' to filter orders |  |  |  | P48013
3 |  | You can create query or watchlist to facilitate quicker alerts |  |  |  | P31225
4 |  | Scenario: How to check whether components have been issued partially to that order? |  |  |  | P48013
5 |  | Locate your WO and go to row exit, partslist. 'Issued' quantity will be updated as & when issues happen |  |  |  | P48013
6 |  | Scenario: How to check status on the dispatch list? There is an application and report |  |  |  | P31220
7 |  | Using application P31220, filter your workcenter and press find. Change the date range to get wider data |  |  |  | P31220
End

## MFG026
MFG026
Production Cost Inquiry and Manager's update to status 95
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: WO status is at 90 when it's complete. Manager need to review the order is correctly updated with material issues/labor before accounting takes over |  |  |  | P48013 |  |  | 90
2 |  | Using Shopfloor workbench, query orders by status range and requested date. You can use <'date' to filter orders |  |  |  | P48013
3 |  | You can create query or watchlist to facilitate quicker alerts |  |  |  | P31225
4 |  | Scenario: How to check whether components have been issued partially to that order? |  |  |  | P48013
5 |  | Locate your WO and go to row exit, partslist. 'Issued' quantity will be updated as & when issues happen |  |  |  | P48013
6 |  | Scenario: How to check whether routing labor is correctly updated?
7 |  | Locate your WO and go to row exit, routing. 'run labor' hours will be updated as & when super backflush is completed
8 |  | Using P31022 production cost inquiry, you can compare standard vs actuals |  |  |  | P31022
9 |  | If the WO completion data is correct, update the WO status to 95. This applied to both WO and WR types |  |  |  | P48013 |  |  | 95
10 |  | Cost accounting will take over these orders from 95 to their process of 96 to 99. No additional materials or labor can be consumed at that time to these orders
End

## MFG027
MFG027
Manufacturing Repair orders
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: Major repair work need to be done on an assembly or on a RMA item |  |  |  | P48013
2 |  | Open Repair WO application and press add |  |  |  | P48013
3 |  | Enter the item, quantity and requested date
4 |  | Press save to get WR order# | WR | [5 empty] | 10
5 |  | Locate your order from the application. Select the row, go to row exit to partslist
6 |  | On form exit, use either copy WO or copy bom option
7 |  | Once the bill is copied into the order, make changes. Press save
8 |  | Optional:Locate your order from the application. Select row, go to row exit to routing
9 |  | Optional:On form exit, use either copy WO or copy routing option
10 |  | Optional:Once the routing is copied into the order, make changes. Press save
11 |  | Go back and verify all necessary updates on done to this order
12 |  | Execute attach partlist/routing version that updates status to 40 but does not append bills/routings again. Or manually update the status to 40 | [6 empty] | 40
13 |  | Using WO inventory issues, complete inventory issues |  |  |  | P31113
14 |  | Using WO completion application, report the completion |  |  |  | P31123 |  |  | 90
15 |  | Assumption: No actual labor usage need to be tracked
16 |  | Check cardex/inventory ledger for IC and IM transactions |  |  |  | P4111
End

## MFG028
MFG028
Workorders for DE-KITTING
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: reconfiguring one product to another |  |  |  | P48013
2 |  | Open Repair WO application and press add |  |  |  | P48013
3 |  | Enter the item, quantity and requested date
4 |  | Press save to get WR order# | WR | [5 empty] | 10
5 |  | Locate your order from the application. Select the row, go to row exit to partslist
6 |  | On form exit, use either copy WO or copy bom option
7 |  | Once the bill is copied into the order, make changes. Press save
8 |  | Optional:Locate your order from the application. Select row, go to row exit to routing
9 |  | Optional:On form exit, use either copy WO or copy routing option
10 |  | Optional:Once the routing is copied into the order, make changes. Press save
11 |  | Go back and verify all necessary updates on done to this order
12 |  | Execute attach partlist/routing version that updates status to 40 but does not append bills/routings again. Or manually update the status to 40 | [6 empty] | 40
13 |  | Using WO inventory issues, complete inventory issues |  |  |  |  | P31113
14 |  | Using WO completion application, report the completion |  |  |  |  | P31123 |  | 90
15 |  | Assumption: No actual labor usage need to be tracked
16 |  | Check cardex/inventory ledger for IC and IM transactions |  |  |  |  | P4111
End

## MFG029
MFG029
Workorders for outside operations
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: system can automatically generate outside operations purchase order (OO type) either from product routings (or) from WO routings. Example: arm200 to arm400 conversion. The conversion cost is built as D1 cost. WO issued at *400 item level, and WO material issued at *200 level |  |  |  | P48013
2 |  | Step1: if the product routing has predefined outside operations steps. Generate WO PL/Rtg. System will generate OO order automatically. |  |  |  | P48013
3 |  | Review the output R31415 to show the purchase order details. Both WO and PO has reference to each other
4 |  | Step2: if the product routing does not have outside ops step, but planner wants to create it now
5 |  | Open WO after PL/Rtg has been attached. Go to routing and add outside operations WC step. Go to row exit and add supplier/cost type.
6 |  | Save the record. Go back to routing, row exit> generate PO.
7 |  | System will generate PO online and will show the order number
8 |  | You can go to regular PO application to modify & process the PO further
9 |  | When the PO is received, system will prompt to update the WO (optional step to indicate planner)
End

## MFG030
MFG030
Component scrap
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: you issued more materials to compensate component scrap |  |  |  | P31116
2 |  | Open comp scrap application and enter item number. It will retrieve all WO |  |  |  | P31116
3 |  | Locate the WO against which this scrap need to be reported |  |  |  | P31116
4 |  | Enter scrap quantity and press save |  |  |  | P4111
5 |  | Inquire item ledger/cardex for this item |  |  |  | P4111
6 |  | Verify cardex transaction under IO doc type |  |  |  | P4111
7 |  | This transaction is available only in Cardex (not in GL) for data analysis and reporting
End

## MFG031
MFG031
WO shortage reports
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: WO shortage can be inquired anytime using Bill inquiry mode. You can even change quantities to check the availability of components |  |  |  | P3002
2 |  | Scenario: But if you release WO just for planning purchases and want to know the real shortages, then WO print gives individual WO shortages |  |  |  | R31418
3 |  | If you need one consolidated shortage report across multiple workorders, you can run this report manually anytime |  |  |  | R31418
4 |  | Execute the report from the menu. Enter/change Dataselection for the Workorders range (or) multiple WO |  |  |  | R31418
5 |  | Review the output. It shows WO level shortage and also one consolidated view below |  |  |  | R31418
6 |  | Push/pull report: use oneview planning analysis inquiry
End

## MFG032
MFG032
Process Workorders: Reversal
(example: sub-assemblies)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: WO completed was for the wrong part and need to be reversed.
2 |  | Assumption: WO is at 90 or 95 status. Do not reverse WO after 95 status. Each of reversal steps have to be done manually
3 |  | Open WO completion application. Locate your order. Enter negative quantity completion. System will give soft warmings. Enter the loc/SN from the original completion record. Press save |  |  |  | P31114
4 |  | Open WO material issues application. Locate the order; enter/add component lines with negative quantities. Use the same loc/SN if applicable. Press Save |  |  |  | P31123
5 |  | If the WO has labor reported, open the labor entry application. Add the transaction for this WO but enter negative hours. | WO |  |  | P31123
6 |  | Move the WO status to 40. you have effectively reversed all transactions and the order is ready again for completions. |  |  |  | P31123
7 |  | Inventory transaction validation: Go to item ledger (cardex) and locate IC transaction for this order |  |  |  | P4111
8 |  | Inventory transaction validation: Go to item ledger (cardex) and locate IM transaction for this order |  |  |  | P4111
END

## MFG033
MFG033
WO Oneview inquiries
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | JDE has standard oneview inquires to research or analyse WO transactions. Open OneView WO analysis application from the menu |  |  |  | P48270
2 |  | Enter branch and press find. Provide additional filters as needed.
3 |  | go to row exit, to view regular built-in reports
4 |  | Customize the grid to suit your needs for future use
5 |  | similar Oneview inquiry exists for planners. Use Oneview planning analysis |  |  |  | P48290
End

## MFG034
MFG034
Understanding forecast consumption
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: if we are using forecasting at the FG level, then system can automatically reduce the actual orders against the forecast and plan rest of the demand into the month
2 |  | Assumption: forecast at FG level exists. Sales orders are received during the period (month)
3 |  | Open S&D inquiry for the product
4 |  | System will show FCST consumption period and net the Sales orders already shipped against the forecast
5 |  | MRP planning will happen only for the rest of quantities within the forecast period
End

## MFG035
MFG035
MRP- net change process
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: you processed lot of MRP messages (with variation in qty/dates) and want to know the results instead of waiting for next day
2 |  | Use P3402, and inquire on your AB# and branch. This will show all net change impact with flags |  |  |  | P3402
3 |  | Execute MRP-net change batch |  |  |  | R3483
4 |  | On the data selection, enter your items that are impacted
5 |  | On processing options, do NOT change any data
6 |  | Submit the job
7 |  | View output to ensure there are no errors
8 |  | Use P3402, and inquire on your AB# and branch. There will not be any content |  |  |  | P3402
End

## MFG036
MFG036
Lot holds and release
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Open lot master application. Filter data by item number & lot/SN. Note: the item number is the second field |  |  |  | P4108
2 |  | To place an item/lot-SN on hold: select the line. On the lot status code field, enter Q (quarantine) hold |  |  |  | P4108
3 |  | Optional: give a reason code placing this hold |  |  |  | P4108
4 |  | Press save and close the screen |  |  |  | P4108
5 |  | Open lot master application and inquire the item went on hold |  |  |  | P4108
6 |  | Open Inventory availability & enter itemnumber. This lot/SN will show as Q hold and quantity not shown as available |  |  |  | P4108
7 |  | To REMOVE an item/lot-SN on hold: select the line. On the lot status code field, remove Q and enter no value (blank) hold |  |  |  | P4108
8 |  | Optional: give a reason code for releasing this hold |  |  |  | P4108
9 |  | Press save and close the screen |  |  |  | P4108
10 |  | Open lot master application and inquire the hold is released |  |  |  | P4108
11 |  | Open Inventory availability & enter itemnumber. This lot/SN will show as no hold and quantity shown as available |  |  |  | P4108
End

## MFG037
MFG037
Perform Lot trace and track inquiry
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Scenario: JDE captures tracebility forward and backward from transactions without any user inputs. Lot trace/track shows the info for queries/recalls |  |  |  | P41203
2 |  | Enter the component item you want to track; filter the date range and press find |  |  |  | P41203
3 |  | Inquire the data on the grid |  |  |  | P41203
4 |  | Go to bottom tabs to get details on SO or PO or WO as applicable
5 |  | If you need to document the result, there is a report to execute |  |  |  | R41203
6 |  | Enter itemnumber and lot number on the data selection
7 |  | View PDF on the submitted job and save the file locally
End

## MFG038
MFG038
Manufacturing Accounting (proof and final)
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Open WO Entry application and locate orders at status=95 | WO |  |  | P48013 |  |  | 95
2 |  | Verify WO material issues by going into Row exit> WO issues |  |  |  | P48013
3 |  | Verify WO labor hours by going into Row exit > WO routing |  |  |  | P48013
4 |  | Check IC Records in Cardex/Itemledger | IC |  |  | P4111
5 |  | Check IM records in Cardex/Itemledger | IM |  |  | P4111
6 |  | Execute manufacturing accounting proof version |  |  |  | R31802A
7 |  | View output in submitted jobs. Verify the WO status is updated to 96 |  |  |  | R31802A |  |  | 96
8 |  | Execute manufacturing accounting final version |  |  |  | R31802A |  |  | 97
9 |  | View output in submitted jobs. Verify the WO status is updated to 96 |  |  |  | R31802A
10 |  | Review GL batches and approve/post |  |  |  | p0011
11 |  | G/L Review -MFG Acctg |  |  |  | P0011
12 |  | Work With Accounts |  |  |  | P0901
13 |  | G/L Review - by W/O Number |  |  |  | P3106I
End

## MFG039
MFG039
MFG Accounting - No Variances
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Identify WO where status=97 in WO Entry application |  |  |  | P48013 |  |  | 97
2 |  | Verify quantity completed |  |  |  | P48013
3 |  | Check IM Record |  |  |  | P4111
4 |  | Check IC Record |  |  |  | P4111
5 |  | Using production cost inquiry check there are no variances reported
6 |  | Execute mfg Variance Acct - Proof |  |  |  | R31804 |  |  | 98
7 |  | Verify output from submitted jobs
8 |  | Execute mfg Variance Acct - Final |  |  |  | R31804 |  |  | 99
9 |  | Verify output from submitted jobs
10 |  | G/L Review -MFG Acctg |  |  |  | P0011
11 |  | Work With Accounts |  |  |  | P0901
12 |  | G/L Review - by W/O Number |  |  |  | P3106I
End

## MFG040
MFG040
MFG Accounting - with Variances
| User | Process Outline | Doc#/type | Batch# | Pass/Fail | App/Rep | Version | Last Status | Next Status
START
1 |  | Identify WO where status=97 in WO Entry application |  |  |  | P48013 |  |  | 97
2 |  | Verify quantity completed |  |  |  | P48013
3 |  | Check IM Record |  |  |  | P4111
4 |  | Check IC Record |  |  |  | P4111
5 |  | Using production cost inquiry check there are material variances reported
23 |  | Execute mfg Variance Acct - Proof |  |  |  | R31804 |  |  | 98
Verify output from submitted jobs
24 |  | Execute mfg Variance Acct - Final |  |  |  | R31804 |  |  | 99
Verify output from submitted jobs
26 |  | G/L Review -MFG Acctg |  |  |  | P0011
27 |  | Work With Accounts |  |  |  | P0901
28 |  | G/L Review - by W/O Number |  |  |  | P3106I
End